## Test Execution Report
Project Information
Project Name | Zedu API Testing
Module | Authentication
Environment | Staging
Tester | Chidera
Tool | Postman
API Documentation | Swagger
Execution Period | 18th Jun 2026 – 14th Jul 2026
Test Execution Summary |  | Defects Raised
Metric | Count | Bug ID | TITLE | SEVERITY | STATUS
Total Test Cases | 28 | BUG_AUTH_001 | Login API returns 400 instead of documented 401 | Meduim | Open
Executed | 28 | BUG_AUTH_002 | Validation errors return 400 instead of documented 422 | Low | Open
Passed | 13
Failed | 15
Blocked | 0
Not Executed | 0
Pass Rate | 46.4%
Fail Rate | 53.6%
Key Findings:
Observations
Registration functionality worked as expected.
Login with valid credentials returned an access token and user details.
Invalid credentials returned HTTP 400 instead of the documented HTTP 401.
Validation errors returned HTTP 400 instead of the documented HTTP 422.
SQL Injection and XSS payloads were rejected successfully.
Overall Assessment Conclusion
The Authentication module was tested using Postman against the Zedu Staging API.Core authentication functionality, including user registration and successful login, performed as expected. Validation of authentication tokens and user information was successful. Several documentation mismatches were identified between the Swagger specification and the actual API implementation. Specifically, endpoints documented to return HTTP 401 (Unauthorized) and HTTP 422 (Validation Failed) instead returned HTTP 400 (Bad Request). These inconsistencies have been documented as defects for further review. Overall, the authentication module is functionally stable; however, the API documentation should be updated or t he implementation aligned with the documented specification to avoid integration issues for API consumers.